## Slide 1: Civil Sector Capacity Building Initiative in Kazakhstan Инициатива по развитию организаций гражданского общества в Казахстане
21 ноября 2012 г.
Алматы

## Slide 2: Objectives of the Project
Objective 1: Effective functioning platform to implement unified NGO sector development strategy
Objective 2: Improve quality of NGO training and consultant services

## Slide 3: VIII. MAJOR PLANNED ACTIVITIES FOR August-December 2012
Training with international trainer: TOT “
Organizational development”
August 28 -30, 2012
15 Participants, including NGO trainers and consultants, acquired necessary skills in providing OD trainings in the regions

## Slide 4
  Training with local trainer: TOT “Organizational development
  September 4 -6, 2012
  15 Participants, including NGO trainers and consultants, acquired necessary skills in training delivery, working with the large groups, etc.

## Slide 5
Regional trainings of alumni trainers based on the results of two TOTs
September- October
Reporting Deadline November, 1
10 Alumni trainers developed and implemented regional trainings in 10oblasts for50regional NGO leaders, staff, and volunteers, using skills and methods learned at TOTs

## Slide 6
Award for the best alumni trainer’s reports
November 14
2 winners from the 1st TOT and 3 winners from the 2d TOT, each received 350 USD;
A total of, 1750 USD was awarded

## Slide 7
Conference on NGO, Business and Government partnership
November 20
60 participants took part at the conference, including 25 from the NGO sector, 20from business, and 15 government representatives

## Slide 8
Dissemination and promotion of NGO Expertise new website
www.ngoexpert.kz
November-December

## Slide 9
Equipment for the NGO center of expertise was purchased

## Slide 10: Предложение: структура конференции
Лидершип симмуляция (leadership simulation) - 1
Шаг 1: участники входят в зал для лекции и ничего не происходит
Шаг 2: задача лектора спровоцировать аудиторию
Шаг 3: обсуждение происходившего
Шаг 4: мини-лекция о 4 К Адиля Нажама: кооперация, конфронтация, кооптация и комплементация

## Slide 11: Предложение: структура конференции
Лидершип симмуляция (leadership simulation) - 2
Шаг 1: участники делятся на три группы и обсуждают претензии к друг другу
Шаг 2: делятся на три группы, но уже смешиваются. Группы обсуждают, те области в которых они нуждаются друг в друге, и ожидания друг от друга
Шаг 3: определяют области для взаимодействия и работают над action plan
Шаг 4: презентуют action plan

## Slide 12: Steps for conference
Decide with Chevron on the format and the dates of the conference
Invite speakers
Invite participants

## Slide 13: Project visibility
Zona.KZ - http://zonakz.net/articles/49336
DK News - http://dknews.kz/npo-novyjj-otschet-vremeni.htm
Panorama - http://panoramakz.com/index.php?option=com_wrapper&Itemid=66
Zhas Kazakh

## Slide 14: Plans for 2013
4 trainings (2 international – UNDEF + 2 local - CHEVRON) based on the topics identified in the assessment
Website support (CHEVRON)
Development of the virtual “Library” (in Russian and Kazakh language) based on training modules (CHEVRON)
Pilot module (distance education) – 2-week course (CHEVRON)
Alumni annual meeting (UNDEF)

## Slide 15: Ongoing activity
Development of partnerships between the Center and existing networks of NGO development in Europe/CIS.
Capacity development of the university staff (involvement of IAB professors in trainings)
Capacity development of NGO trainers and consultants (through alumni network + trainings)